## Sheet1
Adaptive Multi-LLM Agentic RAG with Dynamic Task Routing and Retrieval Planning
Project Start: | 2026-01-17
Project End: | 2026-05-02
Current Date: | 2026-02-11
Weeks in Progress: | 4
[6 empty] | 2026-01-17 | 2026-01-24 | 2026-01-31 | 2026-02-07 | 2026-02-14 | 2026-02-21 | 2026-02-28 | 2026-03-07 | 2026-03-14 | 2026-03-21 | 2026-03-28 | 2026-04-04 | 2026-04-11 | 2026-04-18 | 2026-04-25 | 2026-05-02
Task | Start Date | End Date | Days | Status | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Research and Planning Stage
Literature Review | 2026-01-17 | 2026-02-03 | 17 | Completed | 100%
Dataset Selection | 2026-01-17 | 2026-01-26 | 9 | Completed | 100%
Langchain Framework Fundamentals Learning | 2026-01-20 | 2026-02-11 | 22 | In Progress | 70%
RAG Fundamentals and Advanced Retrieval Techniques | 2026-01-20 | 2026-02-11 | 22 | In Progress | 25%
Single-LLM Baseline Prototype(No routing, no agent) | 2026-01-25 | 2026-02-10 | 16 | Completed | 100%
Streamlit Basic UI Setup | 2026-01-25 | 2026-02-10 | 16 | Completed | 100%
Pilot Study Documentation | 2026-02-01 | 2026-02-11 | 10 | In Progress | 80%
Technology Stack Finalization | 2026-02-01 | 2026-02-12 | 11 | Completed | 80%
Execution Stage
SQLite Database Schema Design | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
CRUD Operation for Chat Threads | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Conversation State Persistence | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Langgraph Routing Node Implementation | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Multiple LLM Provider Integration (GROQ, OpenAI, etc.) | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Multi-hop Retreival Planning | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
UI Polish and User Experience Improvements | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Review Stage
Evaluation Scripts Development | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Static RAG Pipeline Evaluation | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Full Agentic System Evaluation | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Multi-LLM Delegation Evaluation | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Hallucination Rate Measurement | 2026-01-17 | 2026-05-02 | 105 | Not Started | 0%
Status
Not Started
In Progress
Completed
Formulas:
Start Date = [Start Date, row above]
End Date = [End Date, row above]